# 1️⃣ SOP Title

Event Requirement Checklist SOP – Detailed Planning & Operational Readiness Procedure

# 2️⃣ Department

Banquet / Events

(Co-ordination: Kitchen, F&B Service, Engineering, Housekeeping, Security, Accounts, Front Office)

# 3️⃣ Purpose

To establish a structured checklist system to ensure:

- Complete understanding of client requirements

- Smooth inter-department coordination

- Zero last-minute confusion

- Proper resource allocation

- Professional event execution

Every confirmed event must have a completed Event Requirement Checklist.

# 4️⃣ Scope

Applicable to:

- Weddings

- Corporate conferences

- Social gatherings

- Cocktail events

- Product launches

- Private celebrations

Applies to:

- Banquet Sales Executive

- Banquet Manager

- Event Coordinator

- All operational departments

# 5️⃣ Responsibility

| Position | Responsibility |
| --- | --- |
| Sales Executive | Prepare checklist |
| Banquet Manager | Review and approve |
| Event Coordinator | Update final details |
| Department Heads | Confirm readiness |

# 6️⃣ Step-by-Step Procedure

# PART A – BASIC EVENT DETAILS

## A. General Information

- Event name.

- Client contact details.

- Event date.

- Event start and end time.

- Setup and dismantling timing.

- Estimated guest count.

- Final guarantee count deadline.

# PART B – HALL & SEATING ARRANGEMENT

## B. Layout Planning

- Hall name and area allocation.

- Seating style (round table, theatre, classroom, cocktail).

- Table count and chair requirement.

- Stage size and placement.

- VIP seating requirement.

- Welcome desk arrangement.

# PART C – FOOD & BEVERAGE REQUIREMENTS

## C. Menu Confirmation

- Final menu selection attached.

- Special dietary requests (if any).

- Buffet or plated service.

- Live counter requirement.

- Bar requirement and type.

- Service timing (tea break, dinner, etc.).

Final menu must be documented and approved.

# PART D – AUDIO-VISUAL REQUIREMENTS

## D. Technical Setup

- Sound system requirement.

- Number of microphones.

- Projector and screen requirement.

- Lighting setup details.

- DJ or live band requirement.

- Power backup requirement.

# PART E – DECOR & STYLING

## E. Decoration Details

- Theme or color scheme.

- Floral arrangements.

- Backdrop design.

- Stage decoration.

- Entrance decoration.

- Special props or custom setup.

# PART F – VENDOR COORDINATION

## F. Third-Party Vendors

- Decorator details.

- Photographer details.

- DJ/Entertainment contact.

- Special equipment vendor.

- Entry timing for vendors.

- Electrical load requirements.

# PART G – SECURITY & SAFETY

## G. Safety Measures

- Estimated crowd flow.

- Security personnel requirement.

- VIP security need (if applicable).

- Parking and valet requirement.

- Emergency exit accessibility confirmed.

# PART H – HOUSEKEEPING REQUIREMENTS

## H. Cleanliness Setup

- Pre-event cleaning completed.

- Restroom inspection.

- Extra cleaning staff requirement.

- Waste disposal arrangement.

- Post-event cleaning schedule.

# PART I – FINANCIAL DETAILS

## I. Payment Status

- Advance received amount.

- Balance payment due date.

- Approved discount (if any).

- Additional service charges applicable.

- Billing mode (corporate/individual).

# PART J – FINAL REVIEW & APPROVAL

## J. Cross-Department Sign-Off

- Conduct internal briefing meeting.

- Share checklist with all departments.

- Confirm readiness from each department head.

- Update any last-minute changes.

- Obtain Banquet Manager approval.

Checklist must be finalized at least before event setup timeline.

# 7️⃣ Do’s and Don’ts

### Do’s

✔ Document every requirement clearly
✔ Confirm guest count deadline
✔ Attach finalized menu
✔ Conduct inter-department briefing
✔ Update checklist for changes

### Don’ts

✘ Don’t rely on verbal instructions
✘ Don’t ignore vendor entry timing
✘ Don’t skip safety review
✘ Don’t delay sharing checklist
✘ Don’t assume requirements without confirmation

# 8️⃣ Operational Control Standards

- 100% confirmed events have checklist

- All departments briefed before event

- Final guest count documented

- Financial status verified

- Checklist signed and filed

# 9️⃣ Escalation Matrix

| Situation | Escalate To |
| --- | --- |
| Last-minute major change | Banquet Manager |
| Capacity conflict | Management |
| Vendor coordination issue | Management |
| Safety concern | Security |
| Financial dispute | Accounts |

# 🔟 Documentation / Records Required

- Event Requirement Checklist Form

- Final Menu Copy

- Layout Diagram

- Vendor Details Sheet

- Payment Status Record

- Department Sign-Off Sheet

# 1️⃣1️⃣ Common Mistakes to Avoid

- Incomplete requirement capture

- Not confirming final guest count

- Poor communication with departments

- Ignoring safety considerations

- Not updating checklist after changes

- Weak documentation control